## Exploratory Testing
ET_ID | Area | Scenario Tested | Result / Observation
ET_01 | Signup and Login | Tested signup and login using valid details on the mobile app. | Pass — Signup and login completed successfully.
ET_02 | Onboarding | Checked whether required selections and the Complete Setup button behaved as expected. | Partial — Complete Setup was disabled before selecting a feature-tour option; behavior after selection needs verification.
ET_03 | Calendar | Created a calendar event with valid details and checked whether it appeared on the calendar. | Pass — The event was created successfully and displayed on the calendar.
ET_04 | Calendar Validation | Tried creating an event without a title or without selecting a student. | Pass — Validation messages appeared, and the event was not created.
ET_05 | Calendar Boundary Case | Created or edited an event scheduled outside the visible calendar hours. | Fail — The event was accepted but did not appear in the calendar, although it could be found through search.
ET_06 | Caseload | Created a student record, searched for it, and checked whether an existing student could be edited. | Pass — The student record was created, found through search, and existing details were editable.
ET_07 | Service Time Validation | Entered an end time earlier than the start time while recording a service session. | Fail — The session was accepted and saved with an incorrect one-minute duration.
ET_08 | Accommodation | Tried selecting an accommodation and its associated option for different students. | Fail — The selector displayed “No data found,” and the Option dropdown remained disabled.
ET_09 | Mobile Responsiveness | Checked the student profile, action menus, and navigation elements in the mobile app. | Fail — Profile details were cut off, menus overlapped content, and a status indicator overlapped sidebar options.
ET_10 | Cross-Browser Compatibility | Compared the application behavior in desktop Chrome and Microsoft Edge. | No differences observed in the areas checked; this was not an exhaustive cross-browser test.

## Compatiability Report
Environment - AbleSpace Staging Date - 14th October 2026
Compatiability Report
Area/Feature | Chrome Desktop | Firefox / Edge Desktop | Mobile App | Notes
Signup and login | Pass | Pass | Pass | Signup and login completed successfully across all tested platforms. No issues were observed during the checks performed.
Main workflow — Calendar | Partial / Fail | Partial / Fail | Fail | 1. Mobile email verification banner obstructs approximately 20% of the screen. 2. Events scheduled outside visible calendar hours are not displayed in the calendar view, although they remain searchable.
Main workflow — Caseload | Partial / Fail | Partial / Fail | Fail | 1. Student profile details are cut off horizontally. 2. The three-dot menu overlaps profile content and causes visual glitches.
Forms — Service Time | Partial / Fail | Partial / Fail | Needs Verification / Fail | 1. The mobile logging form requires horizontal scrolling. 2. Earlier testing also identified an invalid time-range validation issue.
Forms — Accommodation | Fail | Fail | Fail | The Accommodation dropdown shows “No data found,” and the dependent Option field remains disabled, blocking the workflow.
Navigation | Partial / Fail | Partial / Fail | Fail | The green status indicator associated with the settings icon overlaps the mobile sidebar when switching sections.
Caseload table controls | Partial / Fail | Partial / Fail | Fail | The column menu button requires repeated taps or a press-and-hold before it responds.
Partial: Some checks passed, but the entire feature was not exhaustively tested. Needs verification: Insufficient evidence to assign a final result.
iPad compatibility | Status | Notes
iPad Mini/Pro | Not Tested | Not Collected